## Sheet1
ID | MoSCow Priority Level * | Sprint | User Type | Wants to… | So that…
1 | 1 | 1 | User/Admin | Login into the system | They can use the application
2 | 1 | 1 | User/Admin | Logout of the system | End the ‘session’ and remove all unsaved changes
3 | 1 | 1 | User/Admin | Reset their password | They can access the application if they have forgotten their password
4 | 1 | 2 | User/Admin | View their upcoming and previous shifts | They can view their upcoming shifts for each week
5 | 3 | 2 | User/Admin | View their total hours for the week | They can view their total hours for each week
6 | 2 | 2 | User/Admin | Add a holiday | Add a holiday so that they are not scheduled to work
7 | 3 | 2 | User/Admin | View their upcoming and previous holidays | View their upcoming and previous holidays
8 | 1 | 2 | User/Admin | View their profile | Can view their information
9 | 1 | 2 | User/Admin | Edit their information | They can make changes to any incorrect information
10 | 2 | 4 | User/Admin | Change their password | They can edit their password if forgotten or want to change it
11 | 3 | 4 | User/Admin | View their training level | They can see their training levels
12 | 4 | NI ^ | User/Admin | Create a profile picture | It makes it easier to remember employees
13 | 1 | 2 | Admin | Create a weekly shifts for all employees | They can easily create a weekly rota for all employees
14 | 1 | 2 | Admin | Edit an individual shift | Any mistakes or changes can be corrected
15 | 1 | 1 | Admin | Create an employee | A new employee can be included in weekly shift creation
16 | 3 | 3 | Admin | View employee information | Gain a better understanding when creating rotas
17 | 3 | 3 | Admin | Edit employee information | Any mistakes or changes can be corrected
18 | 2 | 3 | Admin | Edit individual employee pay | Timesheets and weekly reports can provide more in depth information
19 | 1 | 2 | Admin | Change week and day when creating rotas | Rotas can be created for upcoming days/week and past and future rotas can be viewed
20 | 2 | 3 | Admin | Approve employees hours | Payroll reports can be created
21 | 2 | 3 | Admin | Edit employee's hours | Any mistakes or changes can be corrected
22 | 2 | 3 | Admin | Add an unscheduled shift for employee that wasn't on the rota to work | Payroll reports and user reports are acturate
23 | 3 | 5 | Admin | Change users role | Selected user can access to system can be changed
24 | 3 | 5 | Admin | Add employee training | Users training can be view
25 | 2 | 4 | Admin | Create payroll reports for each indidivual employee or for all employees | Payroll can be easily calucalted based on total hours worked and employee pay